| DEVFLOW TECHNOLOGY Strategic Technology & Digital Solutions Partner | REPRESENTED BY: Prince Gajjar Founder & Chief Executive Officer Website: https://devflow.co.in Document Ref: DFT-OPG-14D-2026 |
| --- | --- |

OFFICIAL CLIENT PROJECT TIMELINE & DELIVERY SCHEDULE ONPOINT GROUP LIMITED Website Redesign & Digital Platform Engineering — 14-Day Delivery Roadmap PROJECT DOMAIN onpointgroup.ng; DELIVERY TIMELINE 14 Calendar Days; PREPARED BY DevFlow Technology; TARGET AUDIENCE OnPoint Group (Nigeria).

01. PROJECT OBJECTIVE & EXECUTIVE SUMMARY

DevFlow Technology will redesign and redevelop the OnPoint Group Limited website into a modern, premium, responsive, high-performance digital platform that clearly communicates OnPoint's business capabilities, strengthens its corporate positioning, improves user experience, and supports future business development. The project includes full UI/UX redesign, responsive frontend development, content integration, technical SEO architecture, performance optimization, cross-browser quality assurance, and zero-downtime production deployment on the primary domain onpointgroup.ng.

02. 14-DAY CALENDAR DELIVERY TIMELINE (DAY 1 TO DAY 14)

Each calendar day has an explicitly assigned technical objective, task breakdown, and verified deliverable to ensure uncompromising project velocity and quality control.

[DAY 01] Discovery & Project Setup PHASE 1: STRATEGY & DISCOVERY Key Activities & Scope of Work: • Conduct final project briefing and alignment with OnPoint stakeholders • Perform in-depth audit of existing OnPoint website assets and legacy content • Confirm core business objectives, brand voice, and digital positioning goals • Finalize comprehensive sitemap and hierarchical page structure • Review available company information, background history, and executive bios • Confirm primary services, subsidiary capabilities, and industry verticals • Identify required third-party integrations, tracking scripts, and contact endpoints • Establish dedicated communication channels and feedback turnaround protocols • Initialize repository, CI/CD pipeline, and staging development environment KEY DELIVERABLE: Approved project structure, comprehensive sitemap, and master development plan..

[DAY 02] Information Architecture & UX Planning PHASE 1: STRATEGY & DISCOVERY Key Activities & Scope of Work: • Finalize global navigation architecture and header/footer taxonomy • Define homepage visual hierarchy and high-impact hero value proposition • Structure individual service page templates and capability breakdowns • Structure industry-specific landing sections and market presentation • Define About / Corporate Company profile structure and leadership presentation • Design frictionless Contact flow and conversion-focused Call-to-Action (CTA) paths • Map end-to-end user journeys for prospective clients, partners, and stakeholders • Establish responsive layout grid, typographic scale, and container standards KEY DELIVERABLE: Approved website information architecture, wireframe flow, and UX structure..

[DAY 03] Homepage UI/UX Design PHASE 2: UI/UX DESIGN SYSTEM Key Activities & Scope of Work: • Design high-impact Hero section with bold editorial typography and primary CTA • Design modern sticky navigation with corporate brand badge and contact trigger • Craft Company Positioning and Executive Overview narrative layout • Design Services Overview modular grid with interactive hover paradigms • Create dynamic Business Statistics and impact metrics display • Design Industry Verticals showcase and market capability layout • Design Strategic Technology Partner feature section highlighting DevFlow partnership • Design Corporate Testimonials, Client Endorsements, and Case Study teasers • Design high-conversion Final CTA banner and multi-column corporate Footer KEY DELIVERABLE: Complete, high-fidelity Homepage UI/UX design mockup and visual layout..

[DAY 04] Inner Page UI/UX Design & Design System Finalization PHASE 2: UI/UX DESIGN SYSTEM Key Activities & Scope of Work: • Design master Services Hub page and individual specialized service layouts • Design corporate About page (Vision, Mission, Core Values, Leadership) • Design dedicated Industry Verticals and market solutions pages • Design specialized Real Estate portfolio and project presentation section • Design Technology Partner & Strategic Alliances ecosystem showcase • Design interactive Contact page featuring inquiry form, location, and direct channels • Design complete tablet and mobile adaptive viewport layouts • Finalize master Design System (color tokens, font pairings, button states, spacing rules) KEY DELIVERABLE: Complete multi-page UI/UX design system and approved responsive interface mockups..

[DAY 05] Frontend Development Begins & Core Framework PHASE 3: FRONTEND ENGINEERING Key Activities & Scope of Work: • Initialize production codebase with modern Next.js / TypeScript component architecture • Configure global design tokens, CSS variables, and bespoke utility system • Build responsive Global Header, dynamic mobile slide-out drawer, and desktop navigation • Build comprehensive multi-column Global Footer with legal links and contact badges • Configure typography scales, font preloading, and iconography library • Establish reusable atomic UI component library (Buttons, Badges, Cards, Modals) • Implement responsive container system and layout wrappers across viewports KEY DELIVERABLE: Fully configured core website framework, global navigation, and reusable UI library..

[DAY 06] Homepage Development & Micro-Interactions PHASE 3: FRONTEND ENGINEERING Key Activities & Scope of Work: • Implement high-impact Hero section with smooth entrance animations and action buttons • Code interactive Services Grid with seamless hover transitions and routing • Implement dynamic Statistics counter module and credibility indicators • Build Industries Showcase with tabbed / modular responsive behavior • Code Strategic Technology Partner section showcasing DevFlow collaboration • Build Testimonials carousel and Case Study highlight components • Implement high-conversion CTA banners and inquiry access points • Enforce strict mobile and tablet touch responsiveness across all homepage sections KEY DELIVERABLE: Fully functional, responsive, interactive Homepage on staging environment..

[DAY 07] Services & Industries Development PHASE 3: FRONTEND ENGINEERING Key Activities & Scope of Work: • Develop master Services directory and categorized capability filters • Build detailed individual service page templates with structured content modules • Develop comprehensive Industry Verticals presentation and sector overviews • Build dedicated Real Estate showcase section with project spotlight layouts • Implement strategic Business Development modules and B2B engagement triggers • Enforce full responsive fidelity across desktop, tablet, and mobile breakpoints KEY DELIVERABLE: Complete, fully responsive Services, Industries, and Real Estate section implementation..

[DAY 08] About, Partnership & Contact Development PHASE 3: FRONTEND ENGINEERING Key Activities & Scope of Work: • Build About OnPoint page (Company Story, Executive Vision, Core Pillars) • Develop Strategic Technology Partner page featuring DevFlow Technology capabilities • Implement Partnership Information and strategic collaboration frameworks • Develop interactive Contact page with multi-field validation and inquiry routing • Integrate asynchronous contact form handler with spam protection and email notifications • Implement direct WhatsApp/Phone call triggers, interactive location map, and social channels KEY DELIVERABLE: Completed About, Partnership, and functional Contact inner pages on staging..

[DAY 09] Content Integration & Feature Completeness PHASE 3: FRONTEND ENGINEERING Key Activities & Scope of Work: • Execute comprehensive integration of all finalized client text, copy, and messaging • Integrate high-resolution imagery, brand marks, and multimedia assets • Verify and test end-to-end contact form submissions and notification delivery • Perform full-site navigation verification and cross-page anchor routing check • Audit and validate all internal hyperlinks, external links, and document downloads • Test all button actions, modal triggers, and interactive states • Integrate required third-party analytics and live chat widgets where applicable KEY DELIVERABLE: Feature-complete, content-integrated staging website ready for technical audit..

[DAY 10] Technical SEO & Search Architecture PHASE 4: TECHNICAL SEO & OPTIMIZATION Key Activities & Scope of Work: • Formulate and inject optimized Meta Titles and Meta Descriptions for every page • Structure strict semantic heading hierarchy (H1, H2, H3, H4) across the site • Assign descriptive, keyword-rich Alt Text to all images and media elements • Construct strategic internal linking graph to maximize crawl depth and page authority • Generate automated dynamic XML Sitemap (`/sitemap.xml`) and production `robots.txt` • Enforce self-referential Canonical URLs to prevent duplicate indexing issues • Configure Open Graph (OG) and Twitter Card social sharing metadata • Inject JSON-LD Structured Data Schema (`Organization`, `WebSite`, `LocalBusiness`, `Service`) • Format content blocks for generative AI search engines (AEO/GEO readiness) KEY DELIVERABLE: Fully configured, SEO-ready and Schema-structured digital platform..

[DAY 11] Performance Optimization & Core Web Vitals PHASE 4: TECHNICAL SEO & OPTIMIZATION Key Activities & Scope of Work: • Compress, convert, and optimize all images into next-generation WebP/AVIF formats • Configure responsive image sizing (`srcset`), priority hero loading, and lazy loading • Execute code minification, bundle tree-shaking, and dead-code elimination • Optimize Google Font delivery with font-display swapping and local caching • Optimize Core Web Vitals metrics (LCP < 2.5s, FID/INP < 100ms, CLS < 0.1) • Configure aggressive browser asset caching and compression headers • Conduct mobile bandwidth throttling tests (Fast 3G/4G simulation) to guarantee instant loads KEY DELIVERABLE: High-speed, performance-optimized website achieving 90+ PageSpeed benchmarks..

[DAY 12] Comprehensive Quality Assurance & Cross-Platform Testing PHASE 5: QUALITY ASSURANCE & TESTING Key Activities & Scope of Work: • Execute cross-device QA testing across Desktop (1920px, 1440px), Tablet (768px, 1024px), and Mobile (375px, 414px) • Conduct cross-browser testing across Google Chrome, Apple Safari, Mozilla Firefox, and Microsoft Edge • Validate all form fields, input masks, validation errors, and success state confirmations • Audit all interactive UI elements, dropdowns, drawer menus, accordions, and hover animations • Perform broken link checker scan across all internal and outbound hyperlinks • Verify font rendering, typography scaling, image clarity, and visual alignment • Conduct basic security review (SSL enforcement, form sanitization, header policies) KEY DELIVERABLE: QA-approved release candidate ready for official client review and walkthrough..

[DAY 13] Client Review, Walkthrough & Final Revisions PHASE 5: QUALITY ASSURANCE & TESTING Key Activities & Scope of Work: • Conduct live guided client walkthrough and presentation of the staging website • Demonstrate all responsive layouts, contact flows, and service presentations • Collect consolidated client feedback through structured review form • Apply approved minor refinements, text adjustments, and visual tweaks • Perform final content verification and sign-off check with OnPoint leadership • Execute final technical sanity checks on all modified components • Obtain official client sign-off and green light for production launch KEY DELIVERABLE: Final client-approved website ready for live production deployment.. ⚠️ CRITICAL REQUIREMENT: Client feedback must be consolidated and submitted within the agreed review window on Day 13 to maintain the scheduled Day 14 production launch.

[DAY 14] Production Deployment, DNS Cutover & Official Handover PHASE 6: PRODUCTION LAUNCH & HANDOVER Key Activities & Scope of Work: • Execute zero-downtime production build and deploy to high-availability global CDN • Configure DNS records (A/CNAME/TXT) and verify domain cutover for `onpointgroup.ng` • Provision and verify automated SSL/TLS security certificates for HTTPS encryption • Verify live production XML Sitemap, robots.txt routing, and canonical domains • Connect and verify Google Analytics 4 (GA4) and Google Search Console indexing • Conduct live production smoke testing (contact forms, links, responsive layouts) • Generate full disaster recovery backup and security snapshot • Deliver project handover documentation, credential vault, and admin guidelines KEY DELIVERABLE: ONPOINTGROUP.NG — LIVE PRODUCTION WEBSITE & OFFICIAL HANDOVER..

03. PROJECT MILESTONE SUMMARY

| Milestone | Target | Key Deliverable & Outcome |
| --- | --- | --- |
| Discovery & Planning | Day 1 | Approved project structure, sitemap, and development plan |
| Information Architecture | Day 2 | Approved website UX hierarchy, wireframes & user journeys |
| Homepage UI/UX | Day 3 | High-fidelity homepage design mockup |
| Complete UI/UX | Day 4 | Complete multi-page UI/UX design system & responsive views |
| Development Begins | Day 5 | Core Next.js website architecture, global header & footer |
| Homepage Complete | Day 6 | Fully functional, responsive homepage on staging |
| Services & Industries | Day 7 | Complete Services, Industries & Real Estate sections |
| Core Pages Complete | Day 8 | About, Strategic Technology Partner & Contact pages |
| Feature Complete | Day 9 | Full content integration, working forms & interactive features |
| SEO Implementation | Day 10 | Meta tags, structured schema, sitemap, and AEO/GEO indexing |
| Performance Optimization | Day 11 | Asset compression, Next.js optimization & 90+ PageSpeed |
| QA Complete | Day 12 | Full cross-browser, cross-device & mobile QA approval |
| Client Approval | Day 13 | Client walkthrough, consolidated feedback & final sign-off |
| Production Launch | Day 14 | onpointgroup.ng LIVE on production domain & official handover |

04. CLIENT REQUIREMENTS & PROJECT DEPENDENCIES

To achieve the aggressive 14-day production launch, timely client collaboration is essential. OnPoint Group Limited should provide the following assets and approvals according to the milestone schedule: ☑ Final Company Profile, Mission, Vision, and Leadership Biographies ☑ Final Service & Industry capability descriptions ☑ Company History, Milestones, and Business Achievements ☑ Official Corporate Contact Information & Designated Inquiry Email Endpoints ☑ High-Resolution Vector Logo files (SVG, PNG) and Brand Guidelines (if any) ☑ High-Quality Corporate, Project, and Team Photography/Media Assets ☑ Client Testimonials, Partner Endorsements, and Real Estate Project Case Studies ☑ Corporate Social Media profile links (LinkedIn, X/Twitter, Instagram, etc.) ☑ Legal & Compliance content (Privacy Policy, Terms of Use, Regulatory Disclaimers) ☑ Required Third-Party Credentials, Form Endpoints, or Tracking API keys ☑ Domain Registrar & DNS Access credentials for `onpointgroup.ng` cutover (by Day 13) ☑ Hosting / Cloud Server access where applicable ☑ Google Analytics 4 & Google Search Console access permissions where applicable

05. PROJECT GOVERNANCE & EXECUTION TERMS

A. Feedback & Approval Process

To maintain the 14-day delivery schedule, DevFlow Technology will work through defined sequential milestones. Client feedback should be strictly:

•  Consolidated: Provided as a single unified feedback document from the OnPoint project lead rather than fragmented communications.

•  Clear & Specific: Containing actionable instructions, exact copy replacements, and specific UI references.

•  Timely: Delivered strictly within the agreed 24-hour review window on milestone review days (Day 4 and Day 13).

•  Scope-Aligned: Limited strictly to the approved project scope and architectural blueprint.

B. Scope Control & Change Management

The above 14-day timeline is based on the currently agreed website scope. Additional pages, major architectural changes, custom software integrations, substantial copy rewrites, or features introduced after formal milestone sign-off may require additional development time and/or commercial adjustment. Minor refinements within the approved scope will be seamlessly incorporated during the designated review stages.

C. Critical Project Condition

IMPORTANT TIMELINE CONDITION: The 14-day timeline is fully achievable subject to timely provision of required content, credentials, feedback, and approvals from the OnPoint Group Limited team. Delays in providing content, access credentials, or approvals will automatically shift the target launch date by a corresponding duration without liability to DevFlow Technology.

06. COMMUNICATION & PROJECT MANAGEMENT PROTOCOLS

•  Dedicated Communication Channel: A private project communication channel (WhatsApp / Slack / Email) for real-time correspondence and rapid Q&A.

•  Daily Asynchronous Progress Updates: Daily end-of-day briefing outlining completed activities and next-day milestones.

•  Milestone-Based Synchronous Reviews: Formal video walkthrough sessions scheduled at UI/UX Completion (Day 4) and Final Staging Review (Day 13).

•  Single Point of Contact (SPOC): Prince Gajjar (Founder & CEO, DevFlow Technology) will directly lead technical delivery alongside OnPoint's designated project manager.

•  Transparent Escalation Pathway: Direct executive access to resolve any technical, creative, or scheduling blockers within 4 hours.

07. FINAL PRODUCTION HANDOVER SPECIFICATION

| ✓ Modern, Custom-Engineered Responsive UI/UX | ✓ Desktop, Tablet & Smartphone Optimization |
| --- | --- |
| ✓ High-Performance Next.js Frontend Framework | ✓ Complete Corporate Content & Media Integration |
| ✓ Technical SEO & Structured Schema Architecture | ✓ PageSpeed & Core Web Vitals Optimization |
| ✓ Comprehensive Cross-Browser Quality Assurance | ✓ Secured Contact Form & Inquiry Routing |
| ✓ Zero-Downtime Live Production Deployment | ✓ Admin Documentation & Final Handover Archive |

08. PROJECT AUTHORIZATION & ACCEPTANCE

| FOR DEVFLOW TECHNOLOGY __________________________________ Prince Gajjar Founder & Chief Executive Officer Date: ____20/08/2026____________ | FOR ONPOINT GROUP LIMITED _____________________________________ Authorized Representative OnPoint Group Limited (Nigeria) Date: ________________________ |
| --- | --- |